## Sheet1
HireUp - Daily Report
Sr.No | Start Date | End Date | Task | Done By
1 | 19/07/21 | 23/07/21 | Project Report • Introduction • Objective • Context level diagram • First level DFD • ERD | Both (Ashish & Nikhil)
2 | 28/08/21 | 31/07/21 | HireUp Index page and contact form | Ashish
3 | 2021-01-08 | 2021-03-08 | Project Report: • Requirement Gathering • Data Dictionary | Both (Ashish & Nikhil)
4 | 2021-08-08 | 15/8/21 | Registration and Login Module 1. Sign Up 2. Login 3. Forget Password 4. Reset Password | Ashish
5 | 18/8/21 | 28/8/21 | User Module 1. User Dashboard 2. User View Details 3. User Settings 4. View Generated Resume | Both (Ashish & Nikhil)
6 | 31/8/21 | 2021-05-09 | Admin Module 1. Admin Dashboard 2. Admin View Students record 3. Admin maintian students placement details 4. Admin view contacts messages | Ashish
7 | 2021-06-09 | 2021-10-09 | Project Report: • Hardware & Software Requirement • Functional & Non-Functional Rquirement • Updated Requirement Gathering • Updated Data Dictinary • User Interface Design • Future Enhancement | Both (Ashish & Nikhil)